## Sheet1
Story ID | Story Name | Description | Priority | Iteration (Sprint) number | Acceptance Criteria | Estimation | Notes | Date started (or planned) | Date finished (or planned)
TA-01 | TA Registration and Login | As a TA, I want to register an account and log in to the system using my ID and password, so that I can securely access my profile and applications. | 1 | 1 | 1. Support TA registration with ID, password and confirmed password. 2. Check duplicate ID and password consistency. 3. Support TA login with registered ID and password. 4. Show error message for invalid login credentials. 5. Redirect to TA dashboard after successful login. | 3 | The login screen is the first page displayed upon launching the program, shared by TAs, MOs, and admin. | 2026.03.18 | 2026.03.26
TA-02 | Browse Available Positions | As a TA, I want to browse available TA positions, so that I can find suitable work. | 1 | 1 | 1. Read and display all available TA positions. 2. Show complete job details: module name, required skills, working hours, and special requirements. | 10 | Need data | 2026.03.20 | 2026.03.29
TA-03 | Apply for Job | As a TA, I want to submit an application for a TA position, so that I can be considered for the role. | 1 | 2 | 1. Create an application record when the "Apply" button is clicked. 2. Prevent duplicate applications for the same job. | 4 |  | 2026.03.24 | 2026.04.04
TA-04 | Applicant Profile | As a TA, I want to create a complete profile, so that MOs can view my qualifications and personal information. | 2 | 2 | 1. Store TA profile data (name, ID, phone, email, skills, experience, self-evaluation) in a .csv file. 2. Display profile on TA's personal homepage. 3. Allow MOs to view TA profiles. | 6 | Need data | 2026.03.25 | 2026.04.05
TA-05 | CV Upload | As a TA, I want to upload my CV, so that MOs can access my detailed experience. | 2 | 2 | 1. Support uploading .txt format CV files. 2. Add a "Download Attachment CV" button on the TA's profile page for MOs to download. | 10 | Need data | 2026.03.25 | 2026.04.05
TA-06 | View and Withdraw My Applications | As a TA, I want to view all jobs I have applied for and withdraw my application if needed, so that I can manage my applications properly. | 2 | 2 | 1. Display a list of jobs the TA has applied for, including module name, status, and application time. 2. Allow TA to select an application and withdraw it. Prevent withdrawal if the application has already been processed (Selected/Rejected). 3. Update the application list immediately after successful withdrawal. | 5 | Need data | 2026.04.01 | 2026.04.11
TA-07 | Status Tracking | As a TA, I want to check my application status, so that I know the outcome of my applications. | 2 | 2 | 1. Display a list of applied jobs with status (Pending/Selected/Rejected). 2. Show a bar chart visualizing the count of applications in each status category. | 7 |  | 2026.04.01 | 2026.04.11
TA-08 | Job Search with Keywords | As a TA, I want to search for TA positions using keywords, so that I can find suitable jobs more quickly. | 3 | 3 | 1. Provide a search bar on the job browsing page. 2. Allow TA to input keywords (e.g., MO name, course name, working hours) to filter available positions. 3. Display filtered job results matching the input keywords. | 5 |  | 2026.04.15 | 2026.04.25
TA-09 | Job Recommendation Suggestions | As a TA, I want the AI to recommend suitable positions, so that I can find relevant jobs efficiently. | 3 | 3 | 1. Accept user input for preferences (e.g., working hours). 2. Analyze TA's profile, job requirements, and user preferences to generate top 3 recommended jobs. | 6 | AI-powered | 2026.04.23 | 2026.05.03
TA-10 | AI-Generated Profile Suggestions | As a TA, I want to get AI-recommended profile writing tips based on my uploaded CV, so that I can complete my Applicant Profile more easily. | 4 | 4 | 1. Provide a button labeled "Generate Profile Suggestions" on the TA's profile page. 2. Check if a CV has been uploaded before triggering the AI. 3. Show a reminder to upload a CV first if no CV is detected. 4. Generate profile writing suggestions based on the uploaded CV for TA to copy and modify. | 6 | AI-powered | 2026.05.10 | 2026.05.20
TA-11 | Profile Optimization Suggestions | As a TA, I want the AI to provide profile optimization suggestions based on a target job, so that I can improve my matching score. | 5 | 4 | 1. Allow selection of a target job. 2. Generate 3-5 missing keywords and suggested phrasing for profile optimization when triggered. 3. Display the optimization suggestions for manual modification. | 6 | AI-powered | 2026.05.10 | 2026.05.20
MO-01 | MO Registration and Login | As a MO, I want to register an account and log in to the system using my ID and password, so that I can securely access my module management functions. | 1 | 1 | 1. Support MO registration with ID, password and confirmed password. 2. Check duplicate ID and password consistency. 3. Support MO login with registered ID and password. 4. Show error message for invalid login credentials. 5. Redirect to MO dashboard after successful login. | 3 |  | 2026.03.18 | 2026.03.26
MO-02 | Check the position I posted | As a MO, I want to view a list of all jobs I have posted, so that I can track their status (e.g., open, filled). | 1 | 1 | 1. Display key job information (course name, status, number of applicants) in a list. 2. Allow MO to click a job to view its detailed page. | 6 | Need data | 2026.03.20 | 2026.03.29
MO-03 | View the applicant list | As a MO, I want to view the list of applicants for a specific job, so that I can start the selection process. | 1 | 1 | 1. Show a list of all TA applicants for a job on the job details page. 2. Display basic applicant information (name, year of study). 3. Allow MO to click an applicant to view or download their full profile and CV. | 5 | Need data | 2026.03.20 | 2026.03.29
MO-04 | Edit/Cancel job information | As a MO, I want to edit the details of a job I posted and close positions that are no longer open, so that I can maintain information accuracy. | 1 | 1 | 1. Allow MO to modify unfilled job details (description, requirements, working hours). 2. Allow MO to manually set a job's status to "Closed". | 6 |  | 2026.03.20 | 2026.03.29
MO-05 | Post a new job vacancy | As a MO, I want to post a new TA job opening, so that students can find and apply for it. | 1 | 2 | 1. Allow MO to fill out a form with mandatory job post fields. 2. Create and publish the new job to TA applicants. 3. Generate a unique ID for each new job. | 5 |  | 2026.03.20 | 2026.03.29
MO-06 | Choose or employ applicants | As a MO, I want to select an applicant for my job, so that I can fill the position and update the system status. | 1 | 2 | 1. Allow MO to click the "Select for Job" button on an applicant's profile. 2. Update the selected applicant's status to "Offered/Hired". 3. Change the job's status to "Filled". 4. Update other applicants' status for this job to "Not Selected". | 4 |  | 2026.03.20 | 2026.04.01
MO-07 | MO Profile Management | As a MO, I want to create and manage my personal profile, so that other users can view and contact me. | 2 | 2 | 1. Store MO profile data (name, ID, phone, email, skills, experience, self-evaluation) in the system. 2. Allow Admin and TA users to view the profile information of the MO who posted a specific job. | 4 | Need data | 2026.03.25 | 2026.04.05
MO-08 | View applicant details | As a MO, I want to view an applicant's detailed profile and download their CV, so that I can evaluate their suitability. | 2 | 2 | 1. Provide a "View CV" button/link on the applicant's profile page. 2. Display applicant profile (name, ID, phone, email, skills, experience, self-evaluation) and a link to download their CV. | 5 | Need data | 2026.04.01 | 2026.04.11
MO-09 | Search Applicants | As a MO, I want to search for applicants by ID or keywords, so that I can quickly locate specific candidates. | 3 | 3 | 1. Provide a search bar on the applicant list page. 2. Allow MO to input applicant ID or keywords to filter results. 3. Display matching applicants based on the search query. | 5 |  | 2026.04.15 | 2026.04.25
MO-10 | Applicant Matching Suggestions | As a MO, I want the system to suggest top matching applicants for a job, so that I can quickly identify suitable candidates. | 3 | 3 | 1. Provide a "Get Matching Applicants" button on the applicant list page. 2. Generate and display the top 3 matching applicant IDs based on job requirements and applicant profile. 3. Allow MO to search for applicants by ID. | 6 | AI-powered | 2026.04.23 | 2026.05.03
MO-11 | Job Keyword Suggestions | As a MO, I want the AI to suggest key skills/requirements from my job description, so that I can set screening criteria efficiently. | 4 | 4 | 1. Allow MO to input a detailed job description into the system. 2. Generate 3-5 core keyword suggestions when the "AI Extract Keywords" button is clicked. | 6 | AI-powered | 2026.05.10 | 2026.05.20
MO-12 | Similar Applicant Suggestions | As a MO, I want the AI to suggest applicants similar to a preferred candidate, so that I don’t miss potential suitable applicants. | 5 | 4 | 1. Allow MO to mark an applicant as "Preferred" on the applicant list. 2. Provide a "Find Similar Candidates" button. 3. Display the top 3 similar applicant IDs when the button is clicked. | 6 | AI-powered | 2026.05.10 | 2026.05.20
ADM-01 | Admin Login | As an Admin, I want to log in with special privileges, so that I can access the administration dashboard. | 1 | 1 | 1. Support Admin login with pre-configured ID and password. 2. Show error message for invalid login credentials. 3. Redirect to administration dashboard after successful login. | 3 | The Admin is a special MO who acts like an academic affairs office and has all the functions that MOs have, such as posting jobs. | 2026.03.18 | 2026.03.28
ADM-02 | User Account Management | As an Admin, I want to manage all user accounts (TA, MO), so that I can handle registration issues or disable accounts if needed. | 2 | 2 | 1. Display a list of all registered users and their basic info. 2. Allow Admin to reset user passwords. 3. Allow Admin to disable user accounts. | 7 |  | 2026.03.28 | 2026.04.08
ADM-03 | Manage All the Job Positions | As an Admin, I want to view and manage all job postings in the system, so that I can maintain oversight and remove inappropriate or outdated posts. | 2 | 2 | 1. Display all open job postings on an "All Jobs" dashboard. 2. Allow Admin to manually set a job's status to "Closed". | 7 |  | 2026.03.28 | 2026.04.08
ADM-04 | Recognize Work Imbalance | As an Admin, I want the system to automatically flag TAs with very high or very low workloads, so that I can proactively balance the work distribution. | 3 | 3 | 1. Display a warning when an MO attempts to hire a TA with multiple existing positions. 2. Suggest alternative qualified candidates with lighter workloads. | 8 |  | 2026.04.28 | 2026.05.08
ADM-05 | Check TA’s Overall Workload | As an Admin, I want to view the overall workload of all hired TAs, so that I can ensure no TA is overloaded and maintain fairness. | 4 | 4 | 1. Display a list of all TAs and the number of positions they hold. 2. Allow sorting the list by workload (number of positions). 3. Highlight TAs whose workload exceeds a defined threshold. 4. Show a bar chart visualizing the number of TAs per workload count. | 8 | Need data | 2026.05.05 | 2026.05.15
ADM-06 | Recruitment Data Visualization Statistics | As an Admin, I want to view recruitment data statistics with visual charts, so that I can analyze the system’s usage efficiency and trends over time. | 5 | 4 | 1. Display "Job Post Volume" with a line chart. 2. Display "Application Volume" with a line chart. 3. Display "Hiring Rate" with a pie chart. | 7 | Need data | 2026.05.05 | 2026.05.15
ADM-07 | 30-day Recruitment Insights | As an Admin, I want to trigger AI analysis via a button to get key insights on recent recruitment data, so that I can understand the system’s performance in the past 30 days. | 5 | 4 | 1. Provide a button labeled "Generate 30-day Insights" to trigger AI analysis. 2. When clicked, the AI analyzes the recruitment data of the past 30 days and generates 3 key insights. | 6 | AI-powered | 2026.05.10 | 2026.05.20
SYS-01 | Unified Dialog System | As a developer, I want a reusable dialog system, so that all user interactions across TA/MO/Admin roles have consistent style and behavior. | 3 | 1 | 1. Support input validation and result feedback. 2. Use reusable and stateless dialog components. 3. Keep dialog style consistent across all roles. | 3 |  | 2026.03.22 | 2026.03.30
SYS-02 | Unified Exception Handling System | As a developer, I want a simple exception handling system, so that unhandled errors are captured, logged, and detailed for troubleshooting. | 3 | 2 | 1. Capture all unhandled exceptions. 2. Log stack trace, timestamp and module. 3. Show clear error details for debugging. | 5 |  | 2026.03.25 | 2026.04.05
DOC-01 | Javadoc | As a developer, I want to access complete, up-to-date Javadoc for all core classes, so that I can quickly understand code logic and collaborate efficiently. | 4 | 4 | 1. Provide complete Javadoc for all public classes and methods. 2. Support generating HTML documentation with search and index. 3. Keep cross-references and descriptions up to date. | 1 | Participated in all four iterations | 2026.03.18 | 2026.05.23
DOC-02 | User Manual | As a first-time end user (TA/MO/Admin), I want a clear, step-by-step user manual with screenshots, so that I can learn to use the system without assistance. | 4 | 4 | 1. Cover all core workflows for TA, MO and Admin. 2. Provide clear step-by-step instructions. 3. Use screenshots to mark key UI elements. 4. Export as PDF with table of contents and page numbers. | 3 |  | 2026.05.18 | 2026.05.23