## Sheet1
Story ID | Story Name | Description | Priority | Iteration (Sprint) number | Acceptance Criteria | Estimation | Notes | Date started (or planned) | Date finished (or planned)
DOC-J01 | Core Class Javadoc Writing | As a backend developer, I want to write Oracle-standard Javadoc for all classes in model (TA/Job), service (TAService/MOJobService), and exception packages (including @author/@version/@param/@return/@throws), So that other team members can quickly understand code logic and reduce collaboration costs. | 1 |  | 1. All public classes/methods have complete Javadoc with no missing key tags; 2. Javadoc has no syntax errors and can generate HTML docs via the javadoc command; 3. The @throws tag accurately covers all exceptions thrown by methods.
DOC-J02 | Javadoc HTML Generation & Optimization | As a documentation developer, I want to generate HTML-format Javadoc (with module indexes and search functions) and commit it to the doc folder in GitHub, So that reviewers can access and check documentation online without local compilation. | 1 |  | 1. HTML docs are accessible via the root index.html file; 2. Docs display the hierarchical relationship of core classes (e.g., model → service dependencies); 3. GitHub preview shows no formatting errors.
DOC-J03 | Javadoc Maintenance & Update | As a module developer, I want to synchronously update Javadoc when adding new classes (e.g., AI skill-matching utility classes) in subsequent iterations, So that documentation remains consistent with the latest code logic and avoids misleading users. | 2 |  | 1. Javadoc for new classes complies with the same standard as existing ones; 2. @see tags in old docs are updated to link to new related classes; 3. No outdated descriptions (e.g., deprecated methods marked).
DOC-U01 | User Manual Framework Design | As a technical writer, I want to design a User Manual framework including "System Introduction - Role Operation Flow - FAQs - Error Prompt Explanations", So that end users (TA/MO/Admin) can quickly locate the guidance they need based on their roles. 1 | 1 |  | 1. Framework covers all three user roles with no missing scenarios; 2. Chapter order aligns with user operation habits (e.g., "Registration → Job Application" for TA); 3. Reserved placeholders for screenshots and step descriptions.
DOC-U02 | Operation Flow & Screenshot Supplement | As a technical writer, I want to add step-by-step instructions (≤5 steps per operation) and interface screenshots (console/Web) for core actions (TA registration/MO job posting), So that end users can follow the manual to complete operations without additional guidance. | 1 |  | 1. Each step description is concise (≤20 words) and uses user-friendly language; 2. Screenshots clearly mark key elements (e.g., input boxes, "Submit" buttons); 3. Error operations (e.g., invalid TA ID) include prompt explanations.
DOC-U03 | Manual Format Unification & Export | As a technical writer, I want to unify the User Manual into PDF format (with navigable TOC and page numbers) and control the file size ≤10MB, So that the manual meets project submission standards and is easy to share. | 2 |  | 1. PDF has no formatting chaos (e.g., broken lines, misplaced images); 2. TOC links jump to the correct pages; 3. File is committed to the docs folder in GitHub.
SYS-D01 | Dialog Framework Design | As a frontend developer, I want to design a unified dialog interface with "menu display - user input validation - operation feedback" functions, So that all role menus (TA/MO/Admin) have a consistent style and reduce user learning costs. | 1 |  | 1. Framework supports integer/string input validation (e.g., filtering non-integer menu selections); 2. Feedback messages follow the format "[Status] Content" (e.g., "[Success] Profile created"); 3. Menus are reusable across roles.
SYS-D02 | Dialog Utility Class Implementation | As a frontend developer, I want to develop the DialogUtil class with static methods (e.g., showMenu(), getValidIntInput(), showSuccessMessage()), So that interface classes can call these methods directly and avoid code redundancy. | 1 |  | 1. All methods in DialogUtil are static and stateless; 2. getValidIntInput() supports custom value ranges (e.g., 1-5 for menu choices); 3. Interface classes have no duplicate dialog code.
SYS-D03 | Web Dialog Adaptation | As a full-stack developer, I want to extend the unified dialog system to "frontend pop-up components + backend JSON responses" for Web apps, So that frontend-backend interaction has a consistent format and simplifies error handling. | 3 |  | 1. Frontend pop-ups have a unified style (error/success/confirmation) with consistent colors/fonts; 2. Backend responses use the JSON format: {"code":200,"message":"Success","data":{}}; 3. Pop-ups support dynamic content rendering.
SYS-E01 | Exception Handler Framework Design | As a backend developer, I want to develop the ExceptionHandler class with unified catching/handling methods (supporting business/system/unknown exceptions), So that scattered try-catch blocks are eliminated and exception handling is standardized. | 1 |  | 1. Core method handleException(Throwable e) correctly classifies exception types; 2. Exceptions are logged to ./log/error.log with timestamps/locations; 3. User-friendly prompts are returned (no technical jargon like "NullPointerException").
SYS-E02 | Exception Integration Across Modules | As a backend developer, I want to call the ExceptionHandler in service/file/view layers to replace scattered try-catch code, So that the entire project uses the same exception handling logic and ensures consistent user prompts. | 1 |  | 1. No scattered try-catch blocks exist in service/file/view modules; 2. All exceptions (e.g., file read errors, invalid TA IDs) trigger consistent prompt styles; 3. Exception logs include complete stack traces for debugging.
SYS-E03 | Exception Extension & Optimization | As a backend developer, I want to update the ExceptionHandler to support exception grading (info/warn/error) when adding new exception types (e.g., AI utility errors), So that different levels of exceptions are logged and prompted appropriately (e.g., "warn" for non-critical errors). | 2 |  | 1. New exceptions (e.g., AISkillMatchException) are correctly caught and classified; 2. Logs are stored in grade-specific files (info.log/warn.log/error.log); 3. Prompt severity matches exception grade (e.g., red for "error").